T Level Industry Placement – Small Team Project Brief

Enhancing biodiversity on the farm

Employer brief

Project Title: Enhancing biodiversity on the farm

Organisation: Oakfield Farm & Education Centre

Contact: Ruth Cameron, Environmental Projects Manager

Sector: Agriculture, Land Management & Production

Format: Small team project – 3-5 students, up to 105 hours (approx. 2-3 weeks)

Project context

Oakfield Farm - a mixed-use holding focused on sustainable farming and education - seeks to enhance biodiversity across marginal land without impacting production. A team of T Level students will survey, research, and propose practical improvements.

Objectives

- Assess current biodiversity across field margins, hedgerows, or buffer zones

- Investigate effective interventions (e.g., wildflower strips, hedgerow restoration, insect habitats)

- Propose practical, farm-viable solutions - visual and narrative

- Create a communications tool for staff or stakeholders

Team tasks

- Initial farm visit and briefing

- Land survey and data collection

- Research biodiversity-enhancement tactics

- Design a draft biodiversity action plan

- Develop a communications resource (e.g., staff briefing sheet, signage, or poster)

- Present findings and recommendations

Expected outputs

- Mapped biodiversity improvement plan

- Short report or presentation with rationale and visuals

- Staff-targeted communications material

Employer role

- The Operations Manager (or equivalent) will clarify how much time they will spend working face-to-face with students.

- Outside of face-to-face time, the employer will provide clear contact routes for clarification and feedback.

- Students are expected to manage their own day-to-day schedule, but will receive regular and focused support and intervention from the employer.

- Wherever possible, the employer will co-locate with students for all or a significant portion of the project.

- Access to farm and field records, and support from farm staff.

- Interim review session and attendance at final presentation.

Provider (Tutor) brief

Overview

This practical project provides students real-world experience in land-based data collection, environmental analysis, and recommendations for improvement-applying technical and employability skills.

Mapped performance outcomes

Aligned to Core and Occupational Specialisms in the City & Guilds specification:

- PO1: Collect, structure, and interpret site data, including environmental indicators

- PO2: Understand land management planning-balancing productivity and ecology

- PO3: Recommend sustainable management strategies

- PO4: Communicate findings using visual mapping and summary documents

Three-week timeline

- Week 1: Briefing, site survey, data gathering

- Week 2: Research interventions, develop draft plan

- Week 3: Finalise plan, communications materials, and deliver presentation

Tutor role

- Embed site and ecological content within technical learning

- Guide safe outdoor and data practices

- Support mapping, communication, and project planning

- Liaise with employer to ensure the project remains on track and students are receiving appropriate support from the employer

Evidence collection

- Field survey logs, sketches, or photos

- Biodiversity plan visuals and text

- Communications deliverables

- Feedback from employer and tutor

- Student reflection notes